## Input
Input | EEF | OPA | Proj Charter | Proj Mgmt Plan | Proj Doc | Biz Doc | Agm | Others
Develop Project Charter | T | T |  |  |  | T | T
Develop Project Management | T | T | T |  |  |  |  | -Output from other processes
Direct & Manage Project Work | T | T |  | T | T |  |  | -Approved change requests
Manage Project Knowledge | T | T |  | T | T |  |  | -Deliverables
Monitor and Control Project Work | T | T |  | T | T |  | T | -Work performance information
Perform Integrated Change Control | T | T |  | T | T |  |  | -Change requests -Work performance reports
Close Project/Phase |  | T | T | T | T | T | T | -Accepted deliverables -Procurement documentation
Plan Scope Management | T | T | T | T
Collect Requirements | T | T | T | T | T | T | T
Define Scope | T | T | T | T | T
Create WBS | T | T |  | T | T
Validate Scope |  |  |  | T | T |  |  | -Verified deliverables
Control Scope |  | T |  | T | T |  |  | -Work performance data
Plan Schedule Management | T | T | T | T
Define Activities | T | T |  | T
Sequence Activities | T | T |  | T | T
Estimate Activity Durations | T | T |  | T | T
Develop Schedule | T | T |  | T | T |  | T
Control Schedule |  | T |  | T | T |  |  | -Work performance data
Plan Cost Management | T | T | T | T
Estimate Cost | T | T |  | T | T
Determine Budget | T | T |  | T | T | T | T
Control Cost |  | T |  | T | T |  |  | -Project funding requirements -Work performance data
Plan Quality Management | T | T | T | T | T
Manage Quality |  | T |  | T | T
Control Quality | T | T |  | T | T |  |  | -Approved change requests -Deliverables -Work performance data
Plan Resource Management | T | T | T | T | T
Estimate Activity Resources | T | T |  | T | T
Acquire Resources | T | T |  | T | T
Develop Team | T | T |  | T | T
Manage Team | T | T |  | T | T |  |  | -Work performance reports -Team performance assessments
Control Resource |  | T |  | T | T |  | T | Work performance data
Plan Communication Management | T | T | T | T | T
Manage Communications | T | T |  | T | T |  |  | Work performance reports
Monitor Communications | T | T |  | T | T |  |  | Work performance data
Plan Risk Management | T | T | T | T | T
Identify Risk | T | T |  | T | T |  | T | -Procurement documentation
Perform Qualitative Risk Analysis | T | T |  | T | T
Perform Quantitative Risk Analysis | T | T |  | T | T
Plan Risk Responses | T | T |  | T | T
Implement Risk Responses |  | T |  | T | T
Monitor Risks |  |  |  | T | T |  |  | -Work performance data -Work performance reports
Plan Procurement Management | T | T | T | T | T | T
Conduct Procurement | T | T |  | T | T |  |  | -Procurement documentation -Seller proposals
Control Procurements | T | T |  | T | T |  | T | -Procurement documentation -Approved change requests -Work performance data
Identify Stakeholders | T | T | T | T | T | T | T
Plan Stakeholder Engagement | T | T | T | T | T |  | T
Manage Stakeholder Engagement | T | T |  | T | T
Monitor Stakeholder Engagement | T | T |  | T | T |  |  | -Work performance data

## Tools
Input | Expert Judgement | Meetings | Data Analysis | Others
Develop Project Charter | T | T |  | -Data gathering -Interpersonal and team skills
Develop Project Management | T | T |  | -Data gathering -Interpersonal and team skills
Direct & Manage Project Work | T | T |  | -PMIS
Manage Project Knowledge | T |  |  | -Knowledge mgmt -Information mgmt -Interpersonal and team skills
Monitor and Control Project Work | T | T | T | -Decision making
Perform Integrated Change Control | T | T | T | -Change control tools -Decision making
Close Project/Phase | T | T | T
Plan Scope Management | T | T | T
Collect Requirements | T |  | T | -Context diagram -Prototypes -Data gathering -Decision making -Data representation -Interpersonal and team skills
Define Scope | T |  | T | -Product analysis -Decision making -Interpersonal and team skills
Create WBS | T |  |  | -Decomposition
Validate Scope |  |  |  | -Inspection -Decision making
Control Scope |  |  | T
Plan Schedule Management | T | T | T
Define Activities | T | T |  | -Rolling wave planning -Decomposition
Sequence Activities |  |  |  | -Precedence diagramming method -Dependency determination and integration -Leads and lags -PMIS
Estimate Activity Durations | T | T | T | -Estimation mtds: Analogous, Parametric, Three-point, Bottom-up -Decision making
Develop Schedule |  |  | T | -Schedule network analysis - Critical path method -Schedule compression -Resource optimization -Leads and lags -PMIS -Agile release planning
Control Schedule |  |  | T | -Critical path method -Schedule compression -PMIS -Resource optimization -Leads and lags
Plan Cost Management | T | T | T
Estimate Cost | T |  | T | -Estimation mtds: Analogous, Parametric, Three-point, Bottom-up -Decision making -PMIS
Determine Budget | T |  | T | -Cost aggregation -Historical information review -Funding limit reconciliation -Financing
Control Cost | T |  | T | -To-complete performance index -PMIS
Plan Quality Management | T | T | T | -Data gathering -Decision making -Data representation -Test and inspection planning
Manage Quality |  |  | T | -Design for X -Data gathering -Decision making -Audits -Problem solving -Quality improvement methods
Control Quality |  | T | T | -Data gathering -Inspection -Testing/product evaluations -Data representation
Plan Resource Management | T | T |  | -Organizational theory -Data representation
Estimate Activity Resources | T | T | T | -Estimation mtds: Analogous, Parametric, Bottom-up -PMIS
Acquire Resources |  |  |  | -Interpersonal and team skills -Pre-assignment -Virtual teams -Decision making
Develop Team |  | T |  | -Recognition and rewards -Individual and team assessements -Colocation -Virtual teams -Communication technology -Interpersonal and team skills -Training
Manage Team |  |  |  | -Interpersonal and team skills -PMIS
Control Resource |  |  | T | -Problem solving -Interpersonal and team skills -PMIS
Plan Communication Management | T | T |  | -Communication requirements analysis -Communication techonology -Communication models -Communication methods -Interpersonal and team skills -Data representation
Manage Communications |  | T |  | -Communciation technology, methods -Communication skills Interpersonal and team skills -PMIS
Monitor Communications | T | T |  | -PMIS -Interpersonal and team skills -Data representation
Plan Risk Management | T | T | T
Identify Risk | T | T | T | -Prompt list - Data gathering -Interpersonal and team skills
Perform Qualitative Risk Analysis | T | T | T | -Risk categorization -Data gathering -Interpersonal and team skills -Data representation
Perform Quantitative Risk Analysis | T |  | T | -Representation of uncertainty -Data gathering -Interpersonal and team skills
Plan Risk Responses | T |  | T | -Contingent response strategies -Data gathering -Interpersonal and team skills -Strategies for threats, opportunities, overall project risk -Decision making
Implement Risk Responses | T |  |  | -Interpersonal and team skills -PMIS
Monitor Risks |  | T | T | -Audits
Plan Procurement Management | T | T | T | -Source selection analysis -Data gathering
Conduct Procurement | T |  | T | -Advertising -Bidder conference -Interpersonal and team skills
Control Procurements | T |  | T | -Claims administration -Audits -Inspection
Identify Stakeholders | T | T | T | -Data gathering -Data representation
Plan Stakeholder Engagement | T | T | T | -Data gathering -Data representation -Decision making
Manage Stakeholder Engagement | T | T |  | -Ground rules -Communication skills -Interpersonal and team skills
Monitor Stakeholder Engagement |  | T | T | -Decision making -Data representation -Communication skills -Interpersonal and team skills

## Output
Input | Proj Mgmt Plan Updates | Proj Docs Updates | Work Perf Data Info Report | OPA Updates | Others
Develop Project Charter |  |  |  |  | -Project charter -Assumption log
Develop Project Management |  |  |  |  | -Project mgmt plan
Direct & Manage Project Work | T | T | T | T | -Issue log -Change requests -Deliverables
Manage Project Knowledge | T |  |  | T | -Lessons learned register
Monitor and Control Project Work | T | T | T |  | -Change request
Perform Integrated Change Control | T | T |  |  | -Approved change requests
Close Project/Phase |  | T |  | T | -Final product -Final report
Plan Scope Management |  |  |  |  | -Scope mgmt plan -Requirements mgmt plan
Collect Requirements |  |  |  |  | -Requirements documentation -Requirements traceability matrix
Define Scope |  | T |  |  | -Project scope statement
Create WBS |  | T |  |  | -Scope baseline
Validate Scope |  | T | T |  | -Accepted deliverables -Change requests
Control Scope | T | T | T |  | -Change requests
Plan Schedule Management |  |  |  |  | -Schedule mgmt plan
Define Activities | T |  |  |  | -Milestone list -Change requests -Activity list -Activity attributes
Sequence Activities |  | T |  |  | -Project schedule network diagrams
Estimate Activity Durations |  | T |  |  | -Duration estimates -Basis of estimates
Develop Schedule | T | T |  |  | -Schedule baseline -Project schedule -Schedule data -Project chalendars -Change requests
Control Schedule | T | T | T |  | -Schedule forecasts -Change requests
Plan Cost Management |  |  |  |  | -Cost mgmt plan
Estimate Cost |  | T |  |  | -Cost esstimates -Basis of estimates
Determine Budget |  | T |  |  | -Cost baseline -Project funding requirements
Control Cost | T | T | T |  | -Cost forecasts -Change requests
Plan Quality Management | T | T |  |  | -Quality metrics
Manage Quality | T | T |  |  | -Quality reports -Test and evaluation documents -Change requests
Control Quality | T | T | T |  | -Quality control measurements -Verified deliverables -Change requests
Plan Resource Management |  | T |  |  | -Team charter -Resource mgmt plan
Estimate Activity Resources |  | T |  |  | -Resource requireemnts -Basis of estimates -Resource breakdown structure
Acquire Resources | T | T |  | T | -Physical resource assignments -Project team assignments -Resource calendars -Change requests -EEF updates
Develop Team | T | T |  | T | -EEF updates - Team performance assessments -Change requests
Manage Team | T | T |  |  | -EEF updates -Change requests
Control Resource | T | T | T |  | -Change requests
Plan Communication Management | T | T |  |  | -Communication mgmt plan
Manage Communications | T | T |  | T | -Project communications
Monitor Communications | T | T | T |  | -Change requests
Plan Risk Management |  |  |  |  | -Risk mgmt plan
Identify Risk |  | T |  |  | -Risk register -Risk report
Perform Qualitative Risk Analysis |  | T
Perform Quantitative Risk Analysis |  | T
Plan Risk Responses | T | T |  |  | -Change requests
Implement Risk Responses |  | T |  |  | -Change requests
Monitor Risks | T | T | T | T | -Change requests
Plan Procurement Management |  | T |  | T | -Procurement mgmt plan -Procurement strategy -Bid documents -Procurement statement of work -Source selection criteria -Make-or-buy decision -Independent cost estimates -Change requests
Conduct Procurement | T | T |  | T | -Selected sellers -Agreements -Change requests
Control Procurements | T | T | T | T | -Closed procurement -Procurement documentation updates -Change requests
Identify Stakeholders | T | T |  |  | -Change requests -Stakeholder register
Plan Stakeholder Engagement |  |  |  |  | -Stakeholder engagement plan
Manage Stakeholder Engagement | T | T |  |  | -Change requests
Monitor Stakeholder Engagement | T | T | T |  | -Change requests